## Sheet1
task id | task effort | task duration | dependency | owner | task name | TRUE
T1 | 2 | 1 |  | Wenkai/Yuan | create and link database | TRUE
T2 | 2 | 1 |  | Cheng/Zihui | set up environment and development tools | TRUE
T3 | 4 | 2 | T1 | Binwu/Jianwei | design database structure | TRUE
T4 | 8 | 4 | T2, T3 | Wenkai/Zihui | implement sign up module | TRUE
T5 | 8 | 4 | T4 | Hui/Cheng | implement log in/log out module | TRUE
T6 | 12 | 4 | T5 | Zeyu/Jianwei/Binwu | implement user binding module | TRUE
T7 | 5 | 2 | T5 | Cheng/Yuan | implement user profile editting and auto-update | TRUE
T8 | 10 | 5 | T6 | Wenkai/Zihui | implement launching lost child/found child event functionality | TRUE
T9 | 2 | 2 | T8 | Hui | implement calling 911 functionality | TRUE
T10 | 12 | 4 | T8 | Zeyu/Binwu/Yuan | implement location tracking and data uploading module | TRUE
T11 | 2 | 2 | T10 | Jianwei | system test | TRUE
T12 |  |  |  |  | Only allow account to log into one device at a time | TRUE
sprint 2 | [5 empty] | FALSE
T13 |  |  |  |  | Notifications on parent end | TRUE
T14 |  |  |  |  | Forbid child status update when offline | TRUE
T15 |  |  |  |  | Multi-language support | TRUE
T16 |  |  |  |  | Dark mode | TRUE
T17 |  |  |  |  | Unlink child | TRUE
T18 |  |  |  |  | Reset password | TRUE
T19 |  |  |  |  | create and authenticate police accounts | TRUE | (no auth)
T20 |  |  |  |  | implement location monitoring module for police | TRUE
T21 |  |  |  |  | write user manual and FAQs | TRUE | (no FAQ)
T22 |  |  |  |  | system test | FALSE
T23 |  |  |  |  | landscape mode
font size